CHAPTER 5

PROCUREMENT PROCEDURES

TABLE OF CONTENTS

Page

5.1 Introduction	3

5.1.1 Methods of Procurement	4

5.1.2 Conflict of Interest	4

5.2 Competitive Proposals  (Administration and Professional Services Contracts)	5

5.2.1 Step-by-Step Selection Procedures for Competitive Proposal	7

5.2.2 Contract Provisions	13

5.3 Micro-Purchases	14

5.4 Construction Services & Materials Contracts	14

5.4.1 Small Purchase Procurement	15

5.4.2 Step by Step Small Purchase Procedures	15

5.4.3 Sealed Bid Procurement	16

5.4.4 Step by Step Sealed Bid Procedures	16

5.4.5 Required Contract Provisions	19

5.4.6 Workers’ Compensation Requirements	19

5.4.7 Bonding Information	20

5.4.8 Changes to a Construction Contract	21

5.4.9  Procurement of Recovered Materials	22

5.5 Non-Competitive Proposal Procurement	22

5.6 Recordkeeping Procedures	23

5.6.1 Micro-purchases	24

5.6.2 Competitive Proposal - Professional Services/Administration Services	24

5.6.3 Construction & Material Purchases	24

5.7 Federal & State Laws Governing Procurement of Services, Supplies and Non-Real Property	24

5.7.1 State Laws & Regulations	24

5.7.2 Federal Laws & Regulations	26

CHAPTER 5

PROCUREMENT PROCEDURES

# 5.1 Introduction

This chapter summarizes the laws, rules, and regulations that apply to procurement of contracted services, goods and materials that are purchased, and equipment that is leased for use on TxCDBG projects.

Procurement is the process through which an entity obtains goods and services from vendors. The federal government has established a set of procurement rules that apply to CDBG-funded projects.  In addition, the State of Texas has enacted a set of regulations that also apply to CDBG contracts. The procurement procedures set forth in this chapter comply with both sets of regulations. In addition to applicable federal and state regulations, many local governments have laws and regulations regarding procurement. Grant Recipients must comply with all local laws governing procurement policies. In the event of conflict between federal, state and local law, the most stringent regulation applies.

A good procurement system should facilitate the Grant Recipient’s ability to:

- Identify and specify standards for the goods or services the Grant Recipient wants to obtain - invitations for bids or requests for proposals must be clearly written and must describe the technical requirements of the equipment or services.

- Obtain an independent cost estimate for the goods or services.

- Seek competitive offers to obtain the best possible quality at the best possible price.

- Promote the maximum use of small, minority-owned and female-owned businesses and Section 3 businesses using other suggestions found in Chapter 10: Civil Rights Requirements of this manual

- Have a quality assurance system that helps ensure [Text deleted] the goods and/or services are received in accordance with the standards set forth in the contract.

- Review all procurements to avoid unnecessary and duplicative purchases and to ensure costs are "reasonable”.

- Use a written agreement that clearly states the responsibilities of each party; the method of contracting (fixed price, cost plus fixed fee, purchase orders, etc.) should be appropriate.

- “Cost-plus-a-percentage-of-cost'' or “percentage of construction cost'' methods of contracting will not be allowed under the CDBG program.  Bids must describe actual work to be completed; TDA will not reimburse these costs if such factors are not delineated.  Any line item for profit, overhead, contingency, or other related terms that do not describe actual work to be performed will not be reimbursed.

- The revised federal guidelines now require negotiations of profit as a separate element of the price for each competitively procured contract or modification (i.e.  administration or professional services, including engineering, architectural, and land surveying, contracts) greater than $50,000 and for each non-competitively procured (sole source) contract or modification greater than $50,000 [Text deleted] (See 2 CFR 200.323)

Grant Recipients must provide adequate documentation to show that the selection process was carried out in an open, fair, uniform and thorough manner and to ensure that federal and state procurement requirements were met.  Failure to maintain proper documentation may result in disallowed costs. These records must include, but are not limited to, the following information:

- Rationale for the method of procurement;

- Solicitation/response;

- Evaluation and selection criteria;

- Contractor selection or rejection; and

- The basis for the cost or price. The Grant Recipient should clearly identify during the procurement process any items included in the bid / purchase that are not included in the TxCDBG contract.

Regardless of the type of procurement used, the Grant Recipient must execute a contract to document the work to be completed, the agreed price, and contractor or provider’s required compliance with all applicable state and federal requirements that Grant Recipient must follow.

TDA recommends that the Grant Recipient’s attorney review bid packets and contracts before execution in order to ensure that all federal and state CDBG requirements, local laws and requirements specific to that municipality or county are incorporated. Certification for construction contracts is included in the sample construction contract as Appendix F.

## 5.1.1 Methods of Procurement

The Grant Recipient must use one of the following methods of procurement:

- Competitive Proposals (Administration/Professional Services) – For purchases where conditions for sealed bid are not appropriate. Preferred method for the procurement of administration and professional services [Text deleted].

- Micro-purchases less than or equal to $2,000– The purchase of supplies or services that are less than or equal to $2,000. For such purchases, Grant Recipients may use simplified acquisition procedures instead of Small Purchase procedures as described below. Grant recipient must, to the extent practicable, distribute these purchases equitably among qualified suppliers.

- Small Purchase – The acquisition of supplies or services greater than $2,000 and less than or equal to $50,000. Small purchase procedures are relatively simple and informal procurement methods for securing services, supplies or other property. Price or rate quotations must be requested from at least three (3) qualified sources.

- Sealed Bids (Formal Advertising) – For purchases greater than $50,000. Preferred method for construction contracts.  Bids are publicly solicited and a firm fixed price contract (lump sum or unit price) is awarded to the responsible bidder whose bid, conforming to all the material terms and conditions of the invitation for bids, is the lowest in price.

- Noncompetitive Proposals – Procurement through solicitation of a proposal from only one source and may be used only under special circumstances which are applicable for all purchase levels.

Source:  2 CFR 200.320.

The Grant Recipient must obtain approval from TDA prior to using any method of procurement not described in this chapter.

## 5.1.2 Conflict of Interest

Grant Recipients of a TxCDBG contract must avoid, neutralize or mitigate actual or potential conflicts of interest so as to prevent an unfair competitive advantage or the existence of conflicting roles that might impair the performance of the TxCDBG contract or impact the integrity of the procurement process.

To prevent conflicts of interest, the Grant Recipient must maintain written standards of conduct covering conflict of interest and governing the actions of its employees engaged in the selection, award, and administration of contracts.  Any person or entity, including any benefitting business, utility provider, or other third party entity that is receiving assistance, directly or indirectly, under a TxCDBG contract or award, or that is required to complete some or all work under a TxCDBG contract in order to meet a National Program Objective, or that might potentially receive benefits from TxCDBG awards, may not participate in the selection, award, or administration of a contract supported by CDBG funding. The Grant Recipient may choose to broaden local conflict of interest policies to additional family members and relatives.

A conflict of interest would arise when an employee, officer, agent, consultant, elected or appointed official, any member of his or her immediate family, his or her partner, or an organization which employs or is about to employ any of the parties indicated herein, has an interest or financial interest in or a tangible personal benefit from an entity or individual considered for a contract.

In addition, contractors that develop or draft specifications, requirements, statements of work, or invitations for bids or requests for proposals must be excluded from competing for such procurements.  (See 2 CFR 200.319).  For example, an administrative consulting firm that participates in developing or distributing the request for proposals (RFP) may not then submit a proposal in response to that RFP.

Nepotism and conflict of interest regulations can be found in the Texas Government Code Chapter 573, Texas Local Government Code Chapter 171,  24 CFR 570.489(h), and 2 CFR 200.318(c).

Exception to Conflicts of Interest:  TDA may grant an exception, upon written request from the Grant Recipient, to the conflict of interest provisions on a case-by-case basis if TDA determines that such exception will serve to further the purpose of the TxCDBG project and the effective and efficient administration of the project.  A written request for an exception must be submitted to TDA prior to contract selection award.  (See TxCDBG Application Guide for necessary documentation.)

# 5.2 Competitive Proposals 
(Administration and Professional Services Contracts)

The Competitive Proposal procurement method applies to all administration and professional services contracts paid in whole or in part with TxCDBG funds.

Competitive Proposal procurement is used when conditions are not appropriate for the use of sealed bids and is the preferred method of selection of professional services, such as grant administration, [Text deleted] engineering, architectural, or surveying services. [Text deleted]  Unlike sealed bidding, the competitive proposal method permits consideration of technical factors other than price and negotiation of contract price or estimated cost, and other contract terms and conditions.  All contracts must be awarded to the responsible firm whose proposal is most advantageous to the program, with price and other factors considered.

5.2.0 Procurement - Administration Services and the Professional Services of Engineering/Architectural/Surveying [Section number added]

The steps for procuring administration services (including other professional services), and engineering, architectural, and land surveying services are similar with one major exception.  For the procurement of engineering, architectural, and land surveying services, price may NOT be used as a selection factor and the Grant Recipient must choose the most highly qualified provider of these services on the basis of demonstrated competence and qualifications.  Once the most qualified respondent is chosen, then a fair and reasonable price may be negotiated. See 2 CFR 200.320(d)(5) and Texas Government Code, §2254.004.

In contrast, for administration services and other professional services such as accounting (CPA), grant writing, and real estate appraising (state certified or state licensed), price may be a selection factor and should be taken into consideration.

[Text deleted]

The professional services generally used for CDBG projects means services within the scope of the practice, as defined by state law, of:

- Accounting;

- Architecture;

- Landscape Architecture;

- Land surveying;

- Professional engineering;

- Real estate appraising; or

- Provided in connection with the professional employment or practice of a person who is licensed or registered as:

- A certified public accountant;

- An architect;

- A landscape architect;

- A land surveyor;

- A professional engineer; or

- A state certified or state licensed real estate appraiser.

[Text deleted] All administration and professional services related to TxCDBG projects must be procured competitively, regardless of the source of funds that will pay for the services contracts.

Grant Recipients must adhere to the State of Texas’ Professional Services Procurement Act (Texas Government Code, Chapter 2254.

Other important competitive proposal requirements:

- For all competitive proposal contracts or modifications greater than $50,000, profit must be negotiated as a separate element of price.

- Professional services and administration services paid in whole or in part with TxCDBG funds must use the Step-by-Step procurement procedures described below.

- Professional services and administration services paid solely with local or matching funds must use the TxCDBG process or a competitive procurement process found in local policies.

- Such procurement procedures must be performed prior to the performance of any work by the service contractor. If such procurement procedures are not performed correctly, fees for professional services/administration services will not be eligible for reimbursement with grant funds or count towards community match funds.

- If pre-qualified lists of persons, firms or products are used for acquiring goods and services, the Grant Recipient needs to keep the list current and include enough qualified sources as to ensure open competition.  (2 CFR 200.319(d))

- TxCDBG funds and matching funds may not be used to pay/reimburse for services provided prior to the date of the TxCDBG grant contract with the exception of eligible pre-award costs/activities approved by TDA through the pre-agreement process. The approved pre-agreement costs do not include any services provided prior to submittal of the TxCDBG application.

- If an administration or professional services contractor is preselected and a contract is entered into prior to grant award, the contract should include a statement which states that in the event TxCDBG funds are not awarded to [City/County], the contract shall be terminated by [City/County].

- The cost of preparing a TxCDBG application is an ineligible cost under the CDBG program and therefore is not reimbursable.

The procurement requirements described in this Chapter will not apply to:

- Professional services and administration services performed by an employee of the Grant Recipient; and

- A subrecipient agreement (interlocal agreement) with an agency of the state, such as an agreement with a Council of Governments, whereby a Grant Recipient designates the subrecipient to carry out an eligible activity (such as administration services) for the Grant Recipient. (Chapter 791.001 Texas Government Code)

Engineering Services

The Texas Engineering Practice Act requires most public works projects to be designed, supervised, inspected, and accepted by a registered professional engineer.  If the project is exempt from this requirement under Texas Occupations Code §1001.053, the Grant Recipient must document the exception through a letter certified by the chief local official.

Testing Services

- The Grant Recipient shall determine whether the testing is a component of construction or a professional service, and then should be consistent with that decision in procurement and requests for reimbursement. (For the drilling of ‘test wells’, see also Ch. 7 to determine whether Davis-Bacon labor requirements are applicable in such cases.)

- [Text deleted] Testing Services which require professional services must comply with the State of Texas’ Professional Services Procurement Act (Texas Government Code, Chapter 2254) [Text deleted].

## 5.2.1 Step-by-Step Selection Procedures for Competitive Proposal

Recommendation: To prevent a potential conflict of interest, TDA recommends that Grant Recipients procure service providers - such as administration and engineering or any service provider that may be used to assist the Grant Recipient in its preparation of its TxCDBG application for CDBG funding - before the Grant Recipient files its TxCDBG application for TxCDBG grant funding.

STEP 1 Establish local Selection Review Committee

The Selection Review Committee establishes the criteria or evaluation factors to be used for selection and rating of competing respondents. The committee must include at least one local official, such as a member of the elected governing body. The committee may consist of the entire local governing body, a subset of the governing body, other officers or employees of the locality, or employees or officers of third-party public utilities served through the project. [Text deleted]

The selection committee members shall have no potential conflicts of interest with any of the individuals, firms, or agencies under review (e.g., family relationships, close friendships, business dealings), and no person who might potentially receive benefits from CDBG-assisted activities may  participate in the selection, award, or administration of a contract supported by CDBG funding if he or she has a real or apparent conflict of interest.

STEP 2 Determine the Scope of Services

The scope of work for a professional services or administration services contract describes all desired tasks that a Grant Recipient expects a professional services or administration services provider to perform under a contract.  The scope of work should itemize tasks needed, with timeframes and achievable goals as appropriate and is the basis for the Request for Proposals (RFP)/Request for Qualifications (RFQ) and services contract.

STEP 3 Establish Written Selection Criteria

The committee’s written selection criteria should include, at a minimum, a clear and accurate description of the technical requirements of the services to be procured. Such descriptions shall not contain features that unduly restrict competition.  TDA strongly recommends that the Grant Recipient use a scoring method for reviewing administration and professional services proposals. (See Appendix D and E.)

The specific criteria to be used by the Grant Recipient should fit the needs of the desired services and the specifics of the proposed project.  The importance of each of these factors should be determined before the review process begins by assigning weighted values to each factor.  The local governing body has final authority to approve all professional services and administration services contracts and should be closely involved in the establishment of the written selection criteria. Sample rating sheets for Administration and other Professional Services (other than Engineers/Architects/Surveyors) are found in Appendix D; a sample rating sheet for Engineers/Architects/Surveyors is found in Appendix E.

STEP 4 Develop the Request for Proposals/Qualifications (RFP/RFQ) Package

The Grant Recipient must develop a RFP (Administration and other Professional Services)/RFQ (Engineering/Architectural/Surveying Services) package to issue to potential respondents. RFP/RFQ’s must identify all evaluation criteria factors and their relative importance.

4.1 RFP of Administration and other Professional Services Contracts other than Engineering/Architectural/Surveying Services

The RFP package for Administration/Professional Services must contain three parts.  (Samples of each required documents are found in Appendix D [Text deleted])

1.  Cover Letter: The purpose of this letter is to solicit proposals from interested parties. This can be tailored to the Grant Recipient's specific project.

2.  Request for Proposals (RFP): The RFP provides detailed instructions to respondents and the criteria to be used in evaluating proposals.

The RFP should include the following components:

  - The request for proposal, including specifications and attachments, must clearly describe the scope of services required and identify the factors that will be used to evaluate proposals.

  - Either the Sample Administration/Professional Services Rating Sheet for Administration Services or similar rating sheet with weighted criteria.

And should request the following:

  - A statement of qualifications;

  - Proposed cost of services/fee structure;

  - Related experience with federal programs;

  - Capacity to perform the specific proposed task;

  - Experience in developing and/or implementing civil rights/equal opportunity/Fair Housing activities; and

  - References – a list of past/current clients so that the proposals can be ranked based on past performance.  The selection committee should contact these references and evaluate the respondent’s experience, work performance, and capacity to perform.

  - Proposed costs must be considered in the RFP process.  If the cost of the proposed administration services exceeds $50,000, then profit must be identified and negotiated as a separate element of the contract price.  To comply, the bidder must disclose and certify in its proposal the percentage of profit being used.

It is possible to solicit and procure for application preparation services and administration services in one step.  The RFP must clearly indicate that bids are being solicited for both application preparation and administration services, and must clearly separate the scope and cost of the services associated with preparing an application and the scope and cost associated with administration of the grant.  Costs associated with application preparation services are NOT eligible costs under the TxCDBG program.

3.  Sample Contract:  A sample professional services/administration services contract containing the terms and conditions of the contract between the Grant Recipient and the service provider should be provided as part of the RFP package.  This contract should contain four parts:

  - Part I - Agreement

  - Part II - Scope of Work

  - Part III - Payment Schedule

  - Part IV - Terms and Conditions

Note: Certification Requirement for professional administrators [Text deleted] – Per 4 TAC 30.80, effective date January 1, 2015, professional administrators [Text deleted] need to be certified annually by TDA in order to be eligible to be paid from TxCDBG grant funds or match.  Any person who intends to actually perform grant administration on behalf of a locality must be certified.  Therefore, each person within a firm, who will administer a TxCDBG grant, must be certified by attending a TxCDBG Project Implementation Manual Workshop (or by completing the TxCDBG Project Implementation Manual Workshop webinar online and passing the CDBG review examination).  Grant Recipients need to be aware that professional administration costs will be disallowed if the professional administrator [Text deleted] has not received such annual certification.

4.2 RFQ for Engineering/Architectural/Surveyor Services

1.  Cover Letter: The purpose of this letter is to solicit proposals from interested parties. This can be tailored to the Grant Recipient's specific project.

2.  Request for Qualifications (RFQ): The RFQ for Engineering/Architectural/Surveyor Services provides detailed instructions to respondents and the criteria to be used in evaluating proposals.

The RFQ should include the following components:

  - The request for qualifications, including specifications and attachments, must clearly describe the scope of services required and identify the factors that will be used to evaluate proposals.

  - It is possible to solicit and procure for preliminary engineering services and design engineering services in one step.  A preliminary engineering report (Table 1 of the TxCDBG application) must be prepared by a registered professional, which summarizes the project goals and provides a cost estimate.  The RFQ must clearly indicate that bids are being solicited for both preliminary engineering and design engineering services, and must clearly separate the scope and cost of the services associated with preparing the preliminary engineering report for the TxCDBG application and the scope and cost associated with designing the plans and specifications for the project.

- The RFQ should request that the proposal include/address the following factors:

    - Statement of qualifications;

    - Work experience;

    - Capacity to perform the specific proposed task;

    - Technical expertise;

    - Ability to meet schedules;

    - Proximity to the area of the proposed work;

    - Familiarity with the area of the proposed work;

    - References – list of past/current clients; etc.

3.  Sample Contract: A sample engineering/architecture/surveying services contract containing the terms and conditions of the contract between the Grant Recipient and the service provider should be provided as part of the RFQ package.  This contract should contain four parts:

  - Part I - Agreement

  - Part II - Scope of Work

  - Part III - Payment Schedule

  - Part IV - Terms and Conditions

[Text deleted]

STEP 5 Advertise the RFP/RFQ

In order to create competition for the work, the Grant Recipient must advertise the RFP/RFQ. A sample advertisement is provided that can be altered for the appropriate service. (See Samples in Appendix D and E.)  The Grant Recipient must:

- Advertise in a locally distributed newspaper.

  - To increase and promote participation of small, minority and women owned-business as required below under Step 6, Grant Recipients should email a copy of the solicitation advertisement to TDA at MWBE@texasagriculture.gov.

- The proposal deadline must be no less than 10 (ten) days after the publication of the advertisement and contact date of the RFP/RFQ.

Retain a tear sheet/full-page advertisement/photo copy with publisher’s identification and date/publisher’s affidavit for proof of advertising for monitoring purposes.

STEP 6 Send RFP/RFQ to at least Five (5) Individuals/Firms

Prepare a list of potential firms/individuals. TDA’s list of certified administrators or firms is available on the TDA website, and the Texas Comptroller of Public Accounts’ Historically Underutilized Business (HUB) Directory is available on its website. In accordance with Section 3 of the Housing and Urban Development Act of 1968, successful applicants using CDBG funding for housing or other public construction are required, to the greatest extent feasible, to provide training and employment opportunities to lower-income residents and contract opportunities to businesses in the project area.

Grant Recipients should actively take steps to encourage proposals from small (SBE’s), minority (MBE’s), and woman-owned businesses (WBEs), as well as Section 3 business concerns.  Although Grant Recipients are not directly responsible for meeting a specific minority business participation goal, TDA reports to HUD on the levels of MBE and WBE hiring under all TxCDBG contracts.

Send the RFP/RFQ package to a minimum of five individuals/firms by email, fax, and/or return receipt mail.

  - Document reasons for selecting such individuals/firms for local files.

  - Document evidence of contacting five (5) individuals/ firms.

    - If email/fax, print verifiable evidence that email/fax sent.

    - If mail, send return receipt.

The proposal submission deadline must allow at least 10 days after the RFP/RFQ was sent to these individuals/firms.

STEP 7 Evaluate and Rate the Proposals

After the proposal submission deadline [Text deleted], the selection committee must rate the proposals received by the deadline, using only the specific selection criteria identified in its RFP/RFQ.  This selection process must be thorough, uniform, and well documented through the rating sheets developed in Step 3.

For engineering, architectural, and surveying services, price/cost may not be considered until after the bidder has been chosen.

STEP 8 Select Respondent

The selection committee recommends that the contract be awarded to the respondent with the highest total score (if this method is used) or that has the most qualifications in the proposal evaluation. The recommendation must meet the reasonable, responsive, and responsible tests according to federal procurement procedures:

- Reasonable - Refers to the most suitable, fit and appropriate respondent to accomplish the job in question.

- Responsible - Refers to the respondent that is able to fully perform the requirements of the contract and has the integrity and reliability that will assure good faith performance.

- Responsive - Refers to the respondent that has submitted a bid/proposal that fully conforms to the information requested in the RFP.

The local governing body has the final authority to award contracts and is encouraged to follow the committee’s recommendation, but may select another respondent if the minutes of the local governing body meeting include justification for the selection.  [Text deleted]

The Grant Recipient must award contracts only to responsible contractors possessing the ability to perform successfully under the terms and conditions of a proposed procurement. Consideration will be given to such matters as contractor integrity, compliance with public policy, record of past performance, and financial and technical resources.

Grant Recipients must request TDA’s approval prior to awarding a professional services or administrative services contract if the Scope of Services does not reflect the TxCDBG contract Performance Statement (Exhibit A).

8.1 Selecting the Respondent - For Administration and other Professional Services Contracts other than Engineering/Architectural/Surveyors Services

Determine the most responsive and responsible respondent whose proposal is most advantageous to the program, with price and other factors considered.

The City/County may conduct negotiations with those offerors who are deemed responsive and responsible and fall within a competitive price range, based on the City/County’s evaluation of bidders’ pricing and technical proposals.  After negotiations, these bidders may be given the opportunity to submit a best and final offer.

If the cost of the administration or other professional services exceeds $ 50,000, then profit must be identified and negotiated as a separate element of the price of the contract. To comply, the bidder must disclose and certify the percentage of profit being used.

8.2 Selecting the Respondent - For Engineering/Architectural/Surveying services

Price/cost may not be considered until after the Respondent bidder has been chosen.

Determine the most qualified provider of services on the basis of demonstrated competence and qualifications.

Once the most highly qualified respondent is identified, request a price proposal.  As necessary, negotiate with that provider a fair and reasonable price.

If the cost of the proposed services exceeds $50,000, then profit must be identified and negotiated as a separate element of the contract price.  To comply, the bidder must disclose and certify in its proposal the percentage of profit being used.

If negotiations with the most highly qualified respondent are unsuccessful, formally end negotiations with that provider. Select the next most highly qualified provider and attempt to negotiate a fair and reasonable price.  Repeat this process to select and negotiate with providers until a fair and reasonable priced contract can be awarded.

STEP 9 Clear the Respondent for Federal Requirements

The Grant Recipient must verify the service provider’s eligibility through the System for Award Management (SAM) (www.SAM.gov). Service providers include Council of Governments also known as COGs; COGs must also receive clearance through the SAM website.   Eligibility of all contractors must be verified through the SAM website prior to any formal action authorizing the award of the construction contract to the contractor (examples of formal action include but are not limited to, authorizing resolution, authorizing ordinance, Council approval of award, contract execution, etc.).

Also, if not sent with the TxCDBG application, the Exemption Determination for Activities Listed at 24 CFR 58.34 for Admin/Professional [Text deleted]  Services (See Chapter 3, Environmental Review, Form A303) must be completed and submitted to TDA prior to executing any contract for these services. Note that many Grant Recipients now submit their exemption determinations with their TxCDBG application.  If the Grant Recipient has not submitted its Exemption Determination for Activities Listed at 24 CFR 58.34 for Admin/Professional [Text deleted] Services, then submit the following before the Admin/Professional Services contract is awarded:

- Categorical Exclusion Not Subject to 58.5 ADD and Exempt under 58.34 (Form A303)

[Text deleted]

STEP 10 Approve the Selected Respondent and Award Contract

[Text deleted] Prepare contract for execution by all parties.  (See Sample Contract in Appendix D & E)

Present selection to the City Council/Commissioner’s Court.

City Council/County Commissioner’s Court approves selection of firm/individual.

- The local governing body has the final authority to award contracts but may select another Respondent if the minutes of the local governing body meeting include justification for the selection.

City council/county commissioner’s court approves and executes contract.

- The award and the execution of the contract may/may not occur at the same meeting.

NOTE:  TxCDBG funds and matching funds may not be used to pay/reimburse for services dated prior to the date of the TxCDBG grant contract with the exception of eligible pre-award costs/activities approved by TDA through the pre-agreement process.  The approved pre-agreement costs do not include any services provided prior to submittal of the application.  If a professional services contractor is preselected and a contract is entered into prior to grant award, the contract should include a statement which states that in the event TxCDBG funds are not awarded to [City/County], the contract shall be terminated by [City/County].

STEP 11 Submit Financial Interest Report (A503) within 30 days

Submit the Financial Interest Report (Form A503) to TDA within 30 days of executing the services contract or within 30 days of grant award, whichever is occurs last. This requirement applies to all subcontractors as well. [Text deleted]

## 5.2.2 Contract Provisions

A copy of the service provider contract or agreement must be submitted to TDA, which must include the following at a minimum:

- Names of Both Parties - Grant Recipient and firm.

- Effective Dates - Starting and ending dates.

- Scope of Services - Either directly written into the contract or provided as an attachment that is incorporated into the contract.

- Compensation - Including the maximum amount of the contract as either a firm, fixed-price contract, or a not to exceed cost-reimbursable type contract.

- Local Program Liaison - Identification of a local public official as the consultant's primary contact.

- Amendments - Procedures for amending the scope of work and/or compensation section.

- Termination - Explaining circumstances under which the Grant Recipient or other party can

cancel the contract (e.g., unsatisfactory performance).

- Resolution of Program Non-compliance – Procedures for determining the party responsible for any disallowed costs as a result of non-compliance with federal, state, or program requirements.

If the administrator or other professional service provider is procured before the award of grant funding, then it may be necessary to amend the contract at a later time to provide such contract terms as these details become known.

See Appendix D and E for Sample Bid and Contract Documents for Administration/Professional Services Contracts.

Any changes to the Administration/Professional Services contract price must be documented in the local files through a contract addendum.

# 5.3 Micro-Purchases

For purchases of supplies or services that equal to or less than $2,000, the Grant Recipient may use processes that expedite the transaction and minimize the associated administrative burden.

The purchase orders may be awarded without soliciting any competitive quotations if the Grant Recipient considers the costs to be reasonable and local laws and policies do not prohibit this method of procurement; however, the use of purchase order does not exempt the Grant Recipient from verifying that the contractor is not debarred under the System for Award Management (www.SAM.gov).  The Grant Recipient is required to distribute micro-purchases equitably among qualified suppliers.

For example, a purchase of computer paper in the amount of $1,500 can be treated as “a micro-purchase.”  No competitive quotations would be necessary for the purchase and a price analysis would not be required. However, the Grant Recipient must consider whether to make the purchase from any one of a number of office supply stores. Grant recipients may require that the purchase of computer paper rotate among qualified suppliers if they offer the same rates.

TDA will monitor the use of micro-purchases to ensure that they are not being used to circumvent competitive procurement. Materials and construction should be purchased through small purchase or sealed bids procurement; micro-purchases are generally made for unanticipated costs.

# 5.4 Construction Services & Materials Contracts

Construction services and materials contracts paid in whole or in part with TxCDBG funds must be procured using either the Small Purchase procurement method or the Sealed Bids procurement method. Grant Recipients must comply with TxCDBG program requirements in order to be considered eligible for grant (reimbursement) or match injection.

Environmental clearance must be completed before the Grant recipient executes any construction contract or a materials contract.

## 5.4.1 Small Purchase Procurement

The Small Purchase procurement method uses relatively simple and informal procurement methods to secure equipment, non-professional/non-administrative services, supplies or other property that cost, in the aggregate, less than $50,000 (but greater than $2,000)in accordance with state law.

Key concepts for Small Purchase procurement include:

- Aggregate cost – total cost of the project/job including TxCDBG funds and all other funding sources;

- Job – a project as defined by the engineering plans and specs;

- Separate purchases – purchases, made separately, of items that in normal purchasing practices would be purchased in one purchase;

- Sequential purchases – purchases, made over a period, of items that in normal purchasing practices would be purchased in one purchase;

- Component purchases – purchases of the component parts of an item that in normal purchasing practices would be purchased in one purchase.

The Local Government Code, Sec. 262.023 (c) and Sec. 252.021 specifically prohibit the use of the small purchase procurement method to make separate, sequential, or component purchases of items or services, with the intent of avoiding the competitive bidding and competitive proposal requirements.  For example:

  - A water line job should be one purchase, rather than separate purchases of pipe, fire hydrants, valves, and fittings.

  - A water storage tank should be bid as one purchase, rather than separate purchases of site preparation, foundation, piping, valves, welding, etc.

Prior to beginning small purchase procedures, the Grant Recipient should get an estimate of the cost of the construction from the engineer.  If the estimated cost is greater than $ 50,000, small purchase procurement would not be considered appropriate and is not an allowable cost.

## 5.4.2 Step by Step Small Purchase Procedures

###### STEP 1 Comply with Davis-Bacon Act requirements

The Grant Recipient must obtain prevailing wage rates for the local area as required by the Davis-Bacon and Related Acts, and incorporate those wage rates into the procurement for construction.  See Chapter 7: Davis-Bacon Labor Standards for specific information on the requirements of the Davis-Bacon Act.

###### STEP 2 Contact three vendors for quotes or estimates

The Grant Recipient must contact at least three firms by phone, in person, or in writing including email, to obtain cost estimates for the goods or services.  The responses (including responses that indicate no interest or quotes provided) must be recorded on the Small Purchase Procurement Record (Form A504).

###### STEP 3 Promote participation of MBEs and Section 3 Businesses

The Grant Recipient should actively take steps to encourage proposals from small, minority, and female-owned businesses (MBEs), as well as Section 3 business concerns. Grant Recipients should email a copy of the solicitation advertisement to MWBE@texasagriculture.gov so that SBE/MBE/WBE’s can also be notified by TDA of such opportunities.

STEP 4 Clear the Contractor

The Grant Recipient must verify the construction contractor’s eligibility through the System for Award Management (www.SAM.gov).  See Chapter 7 Davis Bacon Labor Standards for details.  Eligibility of all contractors must be verified through the SAM website prior to any formal action authorizing the award of the construction contract to the contractor (examples of formal action include but are not limited to, authorizing resolution, authorizing ordinance, Council approval of award, contract execution, etc.).

STEP 5 Award the Contract

The Grant Recipient must award the contract to the lowest appropriate bidder. If the contract is awarded to a bidder that does not propose the lowest price, the Grant Recipient must document the decision in compliance with Texas Local Government Code Section 252.043 (municipalities) or Section 262.027 (counties), as applicable.

###### STEP 6 Execute the Contract

The Grant Recipient must submit the Small Purchase Procurement Record (Form A504) and Financial Interest Report (Form A503) to TDA within 30 days of executing the contract, and submit the Labor Standards Record (Form A706) prior to the first Request for Payment for construction work.

## 5.4.3 Sealed Bid Procurement

Procurements of equipment, non-professional services, non-administrative services, materials and construction contracts whose total cost is more than $50,000 must formally advertise for sealed bids in a newspaper of general circulation and hold a public bid opening. Procurements by sealed bids are usually for construction and price is a major factor in awarding these contracts.

[Text deleted]

Sealed bids are publicly solicited and a firm, fixed-price contract (lump sum or unit price) is awarded to the responsible respondent whose bid, conforming with all the material terms/conditions of the invitation for bids, is lowest and best in price (See Appendix F and Appendix G for sample bid and contract documents for construction and material contracts, respectively).

## 5.4.4 Step by Step Sealed Bid Procedures

###### STEP 1 Prepare Bid Package

The Grant Recipient must prepare a bid package detailing the specific goods or services to be provided by the contractor.  This package should provide sufficient technical information for potential bidders to submit a competitive bid. If a construction contract includes both a TxCDBG project and a separate project (not included in the Performance Statement (Exhibit A of the contract) or claimed as match) to be paid by the Grant Recipient or another funding source, the construction contract should clearly indicate the work and the costs associated with each project.

###### STEP 2 Comply with Davis-Bacon Act requirements

The Grant Recipient must obtain prevailing wage rates for the local area as required by the Davis-Bacon and Related Acts and incorporate those wage rates into the construction procurement.  See Chapter 7: Davis-Bacon Labor Standards for specific information on these requirements.

###### STEP 3 Advertise for Bids

The procedure for advertising for bids is as follows:

- Publish once a week for two consecutive weeks prior to bid opening;

- Ensure that the first publication date is at least fourteen (14) days prior to the bid opening date;

- Ensure that the two published notices are at least seven (7) days apart;

- Describe work or item to be purchased or state where specifications can be obtained;

- Include time and place for receiving and opening bids (count fifteen (15) calendar days, not including the print date, from the first advertisement date);

- Include name and position of local official or employee to whom bids are sent;

- Indicate whether bidder should use lump-sum or unit pricing;

- Indicate method of payment by Grant Recipient;

- Indicate type(s) of bond(s) required by the bidder;

- Indicate whether contract will be awarded within thirty (30) or sixty (60) days; and

- Identify TxCDBG contract number.

If an addendum to the bid package is necessary, it must be distributed to each potential bidder. The distribution of an addendum shall be verified either by statements of receipt or registered/certified mail receipts, which shall be included in the public works construction file. The addendum shall allow adequate time for consideration in bid preparation (usually at least one week).  If adequate time is not available, the bid opening date must be extended and the Grant Recipient must republish the invitation for bids containing the place, time, and date for the new bid opening.  Note that any change to the original bid opening date will require republication of the invitation for bids at least once in a locally published newspaper. The republished notice will include the place, time and date for the new bid opening and must be published at least seven days prior to the new bid opening date.

TDA notes that the Dodge Report, Texas Contractor, the Minority Business Development Center, and regional newspapers are resources for advertising bids.

Retain a tear sheet/full-page advertisement/photo copy with publisher’s identification and date/publisher’s affidavit for proof of advertising for monitoring purposes.

See Chapter 10: Civil Rights Requirements for further information on Minority Business Centers.

###### STEP 4 Promote Participation of MBEs and Section 3 Business concerns.

The Grant Recipient should actively take steps to encourage proposals from small, minority, and female-owned businesses (MBEs), as well as Section 3 business concerns. Grant Recipients should email a copy of the solicitation advertisement to MWBE@texasagriculture.gov so that SBE/MBE/WBE’s can also be notified by TDA of such opportunities.

###### STEP 5 Hold the Bid Opening

- Note the date and time of receipt of each bid on the bid envelope, which must be kept with the original bid even following the bid opening;

- Open and read aloud each bid;

- Record the base bid, along with any alternates, on a bid spreadsheet;

- Announce the apparent low bidder and all bidders with complete packets.

The Grant Recipient or its designee (usually the engineer) should carefully review the bids submitted and the low bidder’s statement of qualifications and references.  Awarding the contract on the same date as the bid opening does not generally allow sufficient time to research and review the documents and ensure that the low bidder has provided all the required forms, bonds, certifications, as well as qualifications and references.

- Municipalities are required by state law to award the contract to the lowest responsible bidder based on best value considerations to the municipality. The municipality may reject any and all bids. (Texas Local Government Code Section 252.043(f))

- Counties are required by state law to award the contract to the responsible bidder who submits the lowest and best bid or must reject all bids and publish a new notice. (Texas Local Government Code, Section 262.027(a))

###### Overbids

If the bids received exceed the designated budget, the Grant Recipient has the following options:

- Reject all bids and re-bid the project;

- Accept the deductive alternates in the bid packet (if applicable);

- Delete bid items before contract award, if all bidders agree in writing to changes;

- Accept the low bid and provide additional local funds.

If all bids received exceed the amount of the construction budget, THE GRANT RECIPIENT MAY NOT NEGOTIATE THE CONTRACT PRICE SOLELY WITH THE LOW BIDDER.  To allow one bidder to negotiate the contract price is not fair to the other contractors who submit bids. NEGOTIATION OF THE CONTRACT PRICE SOLELY WITH THE LOW BIDDER WILL RESULT IN THE DISALLOWANCE OF TxCDBG FUNDS FOR CONSTRUCTION COSTS.

Recordkeeping for the Bid Opening

Minutes of the bid opening, along with a tabulation of the bids, must be placed in the contract file. After contract award, the opened bids must be kept on file and available for inspection by anyone desiring to see them. However, any trade secrets and/or confidential information in the proposals are subject to the restrictions of Section 252.049(b) of the Texas Local Government Code and Chapter 552 of the Texas Government Code.

###### STEP 6 Clear the Contractor

The Grant Recipient must verify the construction contractor’s eligibility through the System for Award Management.  See Chapter 7 Davis Bacon Labor Standards for details and www.SAM.gov.

Eligibility of all contractors must be verified through the SAM website prior to any formal action authorizing the award of the construction contract to the contractor (examples of formal action include but are not limited to, authorizing resolution, authorizing ordinance, Council approval of award, contract execution, etc.).

###### STEP 7 Award the Contract

###### The Grant Recipient must award the contract within the number of days indicated in the bid advertisement.

###### STEP 8 Execute the Contract

The Grant Recipient must submit the Bid Tabulation and the Financial Interest Report (Form A503) to TDA within 30 days of executing the contract, and submit the Labor Standards Record (Form A706) prior to the first Request for Payment for construction work.

## 5.4.5 Required Contract Provisions

In all contracts, Grant Recipients and contractors, including engineering, must specifically refer to the project or provide detailed information regarding the work being funded.  In addition to other Federal and State provisions required, all contracts must address, if applicable, the following provisions per 2 CFR 200 Appendix II (See Implementation Manual, Appendix B for required contract provisions):

- Debarment and Suspension (Executive orders 12549 and 12689) – A contract award (see 2 CFR 180.220) must not be made to parties listed on the government wide exclusions list in the System for Award Management (SAM).

- For contracts greater than $10,000, provisions for termination by the Grant Recipient, including the manner by which termination shall be effected and the basis for settlement.

- Access to Records (formerly 24 CFR 85.36 (i)(10))

- Retainage of Records (formerly 24 CFR 85.36(i)(11))

- For contracts greater than $50,000, provisions for administrative, contractual, or legal remedies in instances where contractors violate or breach contract terms, and provide for such sanctions and penalties as appropriate.

In addition to the preceding, Construction Contracts must also address the following:

- For construction contracts greater than $2,000, compliance with the Davis-Bacon Act (40 U.S.C. 3141 et seq.) as supplemented by Department of Labor regulations (29 CFR part 5)(satisfied by inserting HUD 4010 in construction contract; See Appendix B).

- For construction contracts greater than $2,000, compliance with the Copeland “Anti-Kickback” Act (40 U.S.C. 3145) as supplemented in Department of Labor regulations (29 CFR part 3) (satisfied by inserting HUD 4010 in construction contract; See Appendix B).

- For construction contracts greater than $10,000, the inclusion of the Equal Opportunity clause provided under 41 CFR 60-1.4(b).

- For contracts of materials designated in guidelines of the Environmental Protection Agency (EPA) at 40 CFR 247 and greater than $10,000 for the fiscal year, provisions for the procurement of recovered materials.  (2 CFR § 200.322)

- For construction contracts greater than or equal to $100,000, compliance with the Byrd Anti-Lobbying Amendment (31 U.S. C. 1352)

- For construction contracts greater than $100,000, compliance with Contract Work Hours and Safety Standards Act (40 U.S.C. 3701–3708), including work week requirements and safety conditions for workers (satisfied by inserting HUD 4010 in construction contract; See Appendix B).

- Where federal funding exceeds $ 200,000 and the contract or subcontract exceeds $100,000, include Section 3 clause. (24 CFR § 135.38 and 24 CFR § 135.3)

- For contracts greater than $150,000, the Clean Air Act (42 U.S.C. 7401-7671q.) and the Federal Water Pollution Control Act (33 U.S.C. 1251-1387), as amended.

## 5.4.6 Workers’ Compensation Requirements

Texas Labor Code §406.096 requires a governmental entity that enters into a building or construction contract to obtain written certification that the contractor provides workers' compensation insurance coverage for each employee of the contractor employed on the public project. Subcontractors must also provide the governmental entity with proof of coverage. Additionally, the governmental entity must include in bid specifications and contracts specific language and provisions found in 28 TAC §110.110(c)(7). Grant Recipients are responsible for compliance with all applicable statutory policies. The Texas Department of Insurance – Division of Workers’ Compensation regulates and enforces workers’ compensation requirements and may be contacted at 800-372-7713 for more information.

## 5.4.7 Bonding Information

Pursuant to Government Code Chapter 2253, for construction or facility improvement contracts or subcontracts, the minimum bonding requirements for the Grant Recipient which includes a bid guarantee, a performance bond, and a payment bond (if applicable) are as follows:

- A bid guarantee from each bidder equivalent to five percent of the bid price for contracts that is greater than $100,000. The “bid guarantee'' shall consist of a firm commitment such as a bid bond, certified cashier’s check, U.S. Savings bond or other negotiable instrument accompanying a bid as assurance that the bidder will, upon acceptance of his bid, execute such contractual documents as may be required within the time specified.

- A performance bond on the part of the contractor for 100 percent of the contract price for contracts that is greater than $100,000. A “performance bond'' is one executed in connection with a contract to secure fulfillment of all the contractor's obligations under such contract.

The only forms of surety acceptable as a performance bond are:

- Cashier’s Check

- Certified Check

- United States Treasury Bond

- Certificate of Deposit

- Irrevocable Letter of Credit issued by a financial institution subject to the laws of Texas

- Surety or Blanket Bond from a company chartered or authorized to do business in Texas

- A payment bond on the part of the contractor for 100 percent of the contract price. A  “payment bond'' is one executed in connection with a contract to assure payment as required by law of all persons supplying labor and material in the execution of the work provided for in the contract.  Required payment bond(s) must be filed within 30 days from the date of the Notice of Award.

  - Municipalities: If the contract is in excess of $50,000, a payment bond is required. Government Code 2253.021(a)(2)(B)

  - Counties: If the contract is in excess of $25,000, a payment bond is required. Government Code 2253.021 (a)(2)(A)

If the Grant Recipient has adopted an existing bonding policy and requirements that differs from that described above, the Grant Recipient may submit documentation of the existing bonding policy and requirements to TDA with a written request that TDA approve in writing the allowance of utilizing the existing bonding policy and requirements.

If TDA does not determine that its interest is adequately protected and does not provide written approval to the Grant Recipient, the Grant Recipient must adhere to the bonding policy described herein above, pursuant to 2 CFR 200.325 and Government Code Chapter 2253.  All Grant Recipients must ensure that they are meeting all applicable federal, state and local procurement requirements.

## 5.4.8 Changes to a Construction Contract

When changes to a contract are necessary due to decrease or increase in the quantity of work to be performed or of materials, equipment or supplies to be furnished, the Grant Recipient must submit a Construction Change Order Form (Form A505) to TDA.  TDA must approve all change orders to ensure costs are eligible and procured according to TxCDBG requirements. TDA will provide written notification to the Grant Recipient upon review.

To request approval of a proposed Change Order, the Grant Recipient must submit:

- A Construction Contract Change Order  (Form A505), including required chief local elected official’s signature indicating Grant Recipient concurs with the proposed changes.  TDA also recommends that the Grant Recipient obtain the signature of the Project’s Engineer along with any supporting documentation before submitting the Change Order to TDA for its approval.

- Upon approval by TDA of the Change Order, the Grant Recipient then obtains the signature of the construction contractor.

- If a Change Order involves a decrease or an increase of $50,000, the Grant Recipient must receive appropriate approval by the governing body in addition to Construction Change Order (Form A505) (See Local Govt. C., §252.048 (city) and §262.031(county). In such cases, signature by the mayor/county judge on the Construction Change Order A505 represents evidence that such approval from the governing body has been obtained by the City/County.

- Grant Recipient must have sufficient grant or local funds available to meet any increased costs.

- Changes requested that are not directly related to the construction project and/or requesting additional supplies and or activities solely due to unutilized grant funds will not be approved.

- Changes must be appropriate and required for the specific CDBG construction project.

- If a change order includes new items which are not appurtenances, the Grant Recipient must demonstrate competitive pricing.  Approved costs for these items will be eligible up to the amount of the lowest quote received.

Municipalities:

- Change Orders may not increase the original contract price by more than 25% (Tex. Local Gov’t Code 252.048(d)).

- Decreases in the original contract price of more than 25% require written contractor consent.  (Tex. Local Gov’t Code 252.048(d)).

Counties:

- The original contract may not be increased by more than 25% unless required by state or federal law, rule or regulation after the contract is made. (Tex. Local Gov’t Code 262.031(b).

- Grant Recipient must provide written justification, including citation to the appropriate source, for review.

- Decreases to the original contract of more than 18% must have the contractor’s written consent. (Tex. Local Gov’t Code 262.031(b)).

NOTE: Change orders for an increase of more than 25% will be rejected. Grant Recipient must rebid project in the event of an increase of 25% or more.  The State of Texas considers a change in the construction contract price of greater than 25% to be non-competitive, as other potential bidders did not have the opportunity to bid on the true scope of the project during the procurement process.

TDA will not reimburse the Grant Recipient or credit the Grant Recipient’s match commitment for work listed on a Change Order unless the Change Order has been submitted and approved.  Requests for Payment for unapproved change orders will be held at TDA’s discretion.  If the Change Order is executed without TDA approval, the Grant Recipient is obligated to pay for any changes that TDA does not approve.  For these reasons, TDA recommends that the Grant Recipient submit the Change Order prior to fully executing the Change Order.

Grant Recipients must submit all Change Orders on a contract, whether or not the work will be paid with grant or matching funds, so that TDA’s TxCDBG staff has a complete record of the construction contract.  Any difference in price from the Labor Standards Form (Form A706) to the Certificate of Construction Completion (Form A709) must be accounted for by a Change Order.

Project changes reflected in a Change Order may also require an amendment or modification to the TxCDBG contract Performance Statement or Budget (Exhibit A or B to the TxCDBG contract).  These items should be submitted together as described in Chapter 11, Contract Amendments. Prior to executing any Change Order that makes substantial changes to the project and is likely to change the activities, location, or beneficiaries as described in the Performance Statement, the Grant Recipient should contact TDA. TDA will approve a Change Order only when the revised project agrees with the contract Performance Statement.

## 5.4.9 Procurement of Recovered Materials

Pursuant to 2 CFR 200.322, Grant Recipients and their contractors must comply with section 6002 of the Solid Waste Act, as amended by the Resource Conservation and Recovery Act.  The requirements of Section 6002 of the Solid Waste Disposal Act applies to states and local governments using federal funds to procure designated items that are or can be made with recovered materials, and to persons contracting with such entities with respect to work performed under such contracts. The requirements apply if the Grant Recipient purchases $10,000 or more worth of one of the designated recovered materials identified in the EPA guidelines at 40 CFR Part 247 during the course of a fiscal year.  Per 2 CFR 200.322, Grant Recipients should purchase those items that contain the highest percentage of recovered materials practicable, while adhering to competitive bidding processes.  Certain construction materials, like cement and concrete including concrete products such as pipe, are included on the list of designated items. (See 40 CFR 247 for a list of designated items.)

To comply, Grant Recipients should include the Contractors Certification – Recovered Materials (See Appendix F) in its construction bid packets and the list of Texas vendors of recovered materials as found at https://www.epa.gov/smm/comprehensive-procurement-guideline-cpg-program#directory .  Potential construction contractors should then acknowledge such policy and determine whether it is economically feasible to include such recovered materials in its bid.

# 5.5 Non-Competitive Proposal Procurement

Non-competitive proposal procurement (often referred to as “sole source”) may be used when the award of a contract is not feasible under small purchase, sealed bid or competitive proposal procedures. This may be due to single source availability or inadequate competition, determined after solicitation of a number of sources. Non-competitive proposal procurement is most often used for emergency situations and disaster projects.

As discussed, the revised federal guidelines now require negotiations of profit as a separate element of the price for each contract or modification greater than $ 50,000 where there is no price competition. (See 2 CFR 200.323.) To comply with this provision for contracts greater than $50,000, the bidder (Text deleted) must disclose and certify in its non-competitive bid proposal to the Grant Recipient the percentage of profit that is being used in its proposed bid.   For example, the following language may be used by the construction contractor in its proposal: “The undersigned bidder certifies that profit is _____% of labor and materials costs contained in this proposal.”

.

TDA authorizes non-competitive proposals in accordance with federal law. However, all Grant Recipients must receive prior approval from TDA before using non-competitive proposal procurement.  All requests for non-competitive procurement must be submitted in writing by the Grant Recipient.

TDA will consider the use of non-competitive proposal procurement under the following situations (See 2 CFR 200.320(f)):

- Single Source: this method allows procurement through solicitation of a proposal from only one source when the item or service is only available from a single source;

- Public urgency/emergency situations: State laws generally allow noncompetitive negotiations in such cases where the urgency for carrying out the project will not permit delays caused by competitive advertising/solicitation. Grant Recipients requesting such exemptions are those typically funded under the Disaster Relief/Urgent Need Fund;

- After solicitation of a number of sources, competition is determined inadequate. The condition of bids being over budget alone does not create a qualifying condition (inadequate competition) or justification for non-competitive procurement. Grant Recipients must first submit evidence of all public advertisement(s)/solicitations before TDA will consider approving noncompetitive negotiation.

- The Grant Recipient must verify the contractor’s eligibility through the System for Award Management (www.SAM.gov). Eligibility of all contractors must be verified through the SAM website prior to any formal action authorizing the award of the construction contract to the contractor (examples of formal action include but are not limited to, authorizing resolution, authorizing ordinance, Council approval of award, contract execution, etc.) Council of Governments (COGs) must also be cleared through SAM.

# 5.6 Recordkeeping Procedures

The Grant Recipient must maintain records that are detailed enough to show the history of each procurement.  At a minimum, records must demonstrate how the Grant Recipient:

- Executed price sampling for small purchases, or established [published] RFP solicitation;

- Selected the method of procurement and the type of contract to be used;

- Determined the bids or proposals to accept and the ones to reject; and

- Computed the basis for the contract cost or price.

The Grant Recipient must submit a Financial Interest Report (Form A503) for all businesses and other entities contracted to provide products or services in whole or in part for a TxCDBG project, including those that will be wholly or partially paid with other funding sources.  This report:

  - Describes the work to be performed by the business or other entity;

  - Verifies that all required clearances have been completed prior to executing a contract with the business or other entity;

  - Discloses the financial interest of the business or other entity;

  - Provides Minority Business Enterprise information for the business owner (not required for Councils of Government and other non-business entities); and

  - Identifies Section 3 business concerns and anticipated Section 3 employment opportunities.

All contracts for $2,000 or more must be reported on the Financial Interest Report (Form A503). If the contract price changes after the contract is reported, Form A503 does NOT need to be resubmitted.

Financial interests below $2,000 (Micro-purchases by definition) should be disclosed through invoices for grant/match funding – no separate disclosure required.

## 5.6.1 Micro-purchases

The Grant Recipient must maintain copies of all purchase orders and, if possible, show evidence of distributing purchases equitably among suppliers.

## 5.6.2 Competitive Proposal - Professional Services/Administration Services

The Grant Recipient must establish and maintain separate files for records relating to the procurement of a management consultant, engineer or other service provider to detail the procurement process undertaken. The files for professional services or administration services procurement should contain the following information:

- A copy of the Request for Proposals (RFP)

- A copy of the RFP public notice and documentation relating to the distribution of the RFP’s (minimum of five sent) –

  - Email – printout of the sent email with header visible;

  - Fax – confirmation page showing the fax was successfully sent; and

  - Mail – return receipt for certified mail;

- A copy of the RFP cover letter sent to each interested party;

- A copy of each respondent’s reply to the Grant Recipient’s RFP;

- A copy of each respondent’s rating worksheet (if applicable);

- A copy of the procurement summary sheet (if applicable);

- A copy of council/commissioner court action awarding the contract; and

- A copy of the executed professional services or administration contract.

## 5.6.3 Construction & Material Purchases

The Grant Recipient must establish and maintain separate files for records relating to the procurement of a construction contractor or materials supplier to detail the procurement process undertaken. The files for construction and material purchases procurement should contain:

- Bid Document(s) with Labor Standards Provisions included;

- Contract Document(s) with Labor Standards Provisions included;

- Actual Advertisements for Bids (either full page or with publisher's affidavits) or evidence of quotes/estimates received (for small purchase procurement);

- Bids Received (or quotes received);

- Bid Tabulation Sheet(s) (if applicable);and

- A copy of council/commissioner court action awarding the contract

# 5.7 Federal & State Laws Governing Procurement of Services, Supplies and Non-Real Property

The laws and regulations described in this section apply to the procurement of services, supplies or non-real property in TxCDBG-funded projects.

## 5.7.1 State Laws & Regulations

Note: The full text of state statutes may be found online at: http://www.legis.state.tx.us/.

Texas Local Government Code - Chapter 252 (Municipalities) and Chapter 262 (Counties)

###### Chapter 252 Municipal Grant Recipients Construction Bidding Procedures

Municipal Grant Recipients are generally required to conduct competitive sealed bid procurement for any and all contracts over $50,000.

Municipalities are required by state law to advertise their invitation for bids in a newspaper published in the municipality at least once a week for two consecutive weeks.  The date of the first publication must be before the 14th day before the date set to publicly open the bids. If no newspaper is published in the municipality, the notice must be posted at city hall for fourteen days prior to the date of the bid opening. (Texas Local Government Code Section 252.041(a)).

###### Chapter 262 County Grant Recipients Construction Bidding Procedures

County Grant Recipients are generally required to conduct competitive sealed bid procurement for any and all contracts over $50,000.

Counties are required by state law to publish a notice in a newspaper of general circulation in the county at least once a week for two consecutive weeks, with the first day of publication occurring at least fourteen days before the date of the bid opening. If there is no newspaper of general circulation in the county, the notice must be posted in a prominent place in the courthouse for fourteen days prior to the date of the bid opening. (Texas Local Government Code Section 262.025(a)).

Texas Government Code -- Chapter 2253 Public Work Performance and Payment Bonds Covers bonding requirements.

Texas Government Code, Chapter 2254. This chapter is also known as the Professional Service Procurement Act. Chapter 2254 governs the local government procurement of professional services. It prohibits the procurement of architects, engineers, or surveyors based on bid price and requires government entities to first select the most highly qualified provider based on demonstrated competence and qualifications, and then attempt to negotiate with that provider a contract at a fair and reasonable price.

Texas Local Government Code, Chapter 171. This chapter requires local government officials to disclose conflicts of interest and sets forth rules that require officials to abstain where they are in a position to vote or make a decision on any matter involving a business entity or real property for which they have an interest in.

Texas Engineering Practice Act, Chapter 1001, Texas Occupations Code. This Act states that a registered professional engineer must be hired to prepare plans, specifications, and estimates for any public works activities in accordance with this Act. The engineer must directly supervise the project in order to ensure the public health, safety, and welfare; however, this Act does not apply to road maintenance or betterment work undertaken by Counties.

Procurement Standards (Uniform Grant Management Standards (UGMS) - Texas Comptroller of Public Accounts

Conflict of Interest - Nepotism and conflict of interest regulations can be found in the Texas Government Code Chapter 573 and Texas Local Government Code Chapter 171.

## 5.7.2 Federal Laws & Regulations

HUD Conflict of Interest regulations at 24 CFR 570.489(h) and 2 CFR 200.318(c). This regulation sets forth prohibitions against the use of CDBG funds by employees and officials for private gain.

Title 2, Code of Federal Regulations (CFR) Part 200 – 2 CFR 200.317-.326 Procurement Standards and 2 CFR 200.333-.337 Record Retention.   The full text of 2 CFR 200 can be found at

http://www.ecfr.gov/cgi-bin/text-idx?SID=30603de019691a3c1198398480c1fabb&mc=true&node=pt2.1.200&rgn=div5

Title 40, Code of Federal Regulations (CFR) Part 247, Comprehensive Procurement Guidelines for Products Containing Recovered Materials. This guideline designates items that are or can be made with recovered materials.

# Text boxes

A contractor that intends to respond to the Request for Proposals may provide information on TxCDBG procurement procedures, but may NOT participate in the development or drafting of specifications, requirements, statements of work, or invitations for bids or requests for proposals, including, but not limited to, the development of the scoring criteria, the final selection of firms to be contacted, or the scoring of proposals.

Negotiation of price for engineering/architectural/surveyor services must take place after selection is completed; proposed cost may not be a selection criteria or consideration. Proposed costs should not be disclosed by Grant Recipient to such bidders until most qualified bidder has been chosen.

Wage Rates are not required for construction contracts less than $2,000.

Third Party Procurement Services

A Grant Recipient may choose to purchase certain goods and services through a third party, such as the Texas Association of School Boards “Buy Board” or the Houston-Galveston Area Council “HGACBuy”.  All procurement requirements apply to purchases through these entities; however many steps may be conducted by the third party rather than the Grant Recipient.  The Grant Recipient must retain a copy in the contract files of the cooperative agreement with the third party certifying the type of procurement process used.